## Lead
Project Name
Group Number - 6
Team Lead & Frontend Lead- Ravindra
Backend Lead - Ravindra

## Status Track
Project Status Check Report Team - 7
Sl no. | Employee ID | Name | Domain | Module | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17
1 | 2492080 | Shahid Afridi | front-end | customer | Project Overview and solution discussion | Model,Repository | Service, Controller | Exception,Integration | customer Components | Bug Fixing | Group Discussion &PPT
2 | 2492232 | Ravi Kashyap | front-end | sale | Project Overview and solution discussion | Model,Repository | Service, Controller | Exception,Integration | sale Components | Routing | Group Discussion
3 | 2492075 | Pushpashree T | front-end | item | Project Overview and solution discussion | Model,Repository | Service, Controller | Exception,Integration | item Components | BootStrap | Group Discussion
4 | 2491499 | Pulipati Agni Zion Princy | front-end | purchase | Project Overview and solution discussion | Model,Repository | Service, Controller | Exception,Integration | purchase Components | BootStrap | Group Discussion
5 | 2492148 | Pravakar Muduli | front-end | Login/Register | Project Overview and solution discussion | Model,Repository | Service, Controller | Exception,Integration | Login Components | Routing | Group Discussion
6 | 2492360 | Rohini Dattatray Chavhan | back-end | user | Project Overview and solution discussion | Model,Repository | Service | Controller | Exception | Database | Group Discussion
7 | 2492019 | Saurabh Kumar Tiwari | back-end | Customer | Project Overview and solution discussion | Model,Repository | Service | Controller | Exception | Bug Fixing | Group Discussion &PPT
8 | 2492002 | Purusottam Patra | back-end | item | Project Overview and solution discussion | Model,Repository | Service | Controller | Exception | Database | Group Discussion
9 | 2491560 | SathishKumar B | back-end | purchase | Project Overview and solution discussion | Model,Repository | Service | Controller | Exception | Database | Group Discussion
10 | 2492077 | Ravindra Kulakarni | back-end | sale | Project Overview and solution discussion | Model,Repository | Service | Controller | Exception | Bug Fixing | Group Discussion

## Status Meeting
Status Meeting Group - Group-6
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-04-11 | 10:30 | a | 14:30 | a | 18:20 | a
2022-04-12 | 10:00 | a | 13:00 | a | 17:00 | a
2022-04-13 | 10:30 | a | 14:00 | a | 18:10 | a
2022-04-14 | 10:30 | a | 14:30 | a | 18:30 | a
2022-04-15 | 10:15 | a | 14:30 | a | 17:30 | a
2022-04-16 | 10:30 | a | 15:30 | a | 18:30 | a
2022-04-17 | 10:30 | a | 16:30 | a | 19:30 | a
2022-04-18 | 10:30 | a | 16:30 | a | 19:30 | a